Salinas Valley Adult Education Consortium

16-17 Annual Plan Amendments

Submitted May 15, 2017

Changes to Plan under Objective 3: Integration & Seamless Transition

* Due to the urgency of dealing with data and accountability issues, it was decided that the professional learning communities (ESL, Basic Skills, and CTE) would not meet this academic year, but instead a Data Workgroup would be formed to develop and implement the Data & Accountability Plan.
* Hartnell’s bridge programming will end up occurring in the beginning of the 17-18 program year, rather than 16-17.

Changes to Plan under Objective 4: Filling Gaps

* In addition to offering HSE and HSD classes as planned, Gonzales Adult School began an Independent Study option for adult students.
* North Monterey County Adult Education began offering Adult ESL and Parent Education courses via contract with Jump Into English. Soledad Adult School also did some Parent Education, not originally planned. South Monterey County Adult School did not plan to do Family Literacy or Parent Education.
* In February, Gonzales Adult School was allocated an additional $43,700 (out of shared funds originally intended for other purposes, including 15-16 carryover and 16-17 funds) to complete the buildout of one of their Adult Education-dedicated portables, in order to be ADA compliant.
* In February, MCOE - Alternative Education was allocated an additional $37,000 for clerical support staff (out of shared funds originally intended for other purposes, including 15-16 carryover and 16-17 funds).
* The data and assessment software purchases (CASAS TE and ASAP) listed in the Annual Plan were moved to the Data & Accountability Plan.

Changes to Plan under Objective 5: Acceleration

* Salinas Adult School started a Business Office Technology course (CTE), as planned, but decided not to do the Medical Office Technology course at this time.
* Gonzales Adult School started to offer paraprofessional testing (e.g. teacher’s aides) and CPR/First Aid classes.
* In February, an additional $20,000 was allocated to Gonzales Adult School (out of shared funds originally intended for other purposes, including 15-16 carryover and 16-17 funds) for the purchase of a forklift simulator for a new Forklift Certification program they want to begin. The plan was to purchase it by the end of 16-17; however, it may end up being 17-18.
* In February, MCOE - Alternative Education was allocated an additional $30,000 (out of shared funds originally intended for other purposes, including 15-16 carryover and 16-17 funds) to expand several current CTE programs, including Transportation/Aviation/Diesel Mechanics.
* The renewal of our Consortium’s Northstar Digital Literacy Assessment contract was moved from the Annual Plan to the Data & Accountability Plan.